## Sheet1
Id | Project | Task | Sub Task | Activity | Sub Activity | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Responsible | Dependencies | Remarks | Status | Department | Benefits
s | BP | [13 empty] | 10 man days
| BP | Requirement gathering |  |  |  | 2026-02-11 | 2026-02-27 | 2026-02-11 | 2026-02-27 | Ananth & Ivan
|  |  | Business requirement |  |  | 2026-02-11 | 2026-02-13 | 2026-02-11 | 2026-02-13 | Ananth & Ivan
|  |  |  | Process mapping (As‑Is / To‑Be) |  | 2026-02-16 | 2026-02-18 | 2026-02-16 | 2026-02-18 | Ananth
|  |  |  | User journeys (Purchaser, Vendor, MDM) |  | 2026-02-18 | 2026-02-23 | 2026-02-18 | 2026-02-23 | Ananth
|  |  |  | Agent identification & scope |  | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | Ivan
|  |  |  | Validation & business‑rule definition |  | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | Ananth
|  |  | Cost Approval from RDC |  |  | 2026-05-18 | 2026-05-22 |  |  | RDC
|  | Development |  |  |  | 2026-02-25 | 2026-05-22 | 2026-02-25 |  | Us & GITL
|  |  | Frontend |  |  | 2026-02-25 | 2026-05-15 | 2026-02-25 |  | Us & GITL
|  |  |  | Purchaser Form |  | 2026-02-25 | 2026-05-08 | 2026-02-25 |  | Us & GITL
[5 empty] | Mapping of fields | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | Ananth
[5 empty] | Field wise controls and measures | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | Ananth
[5 empty] | Coding | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
|  |  |  | Vendor Form |  | 2026-02-25 | 2026-05-08 | 2026-02-25 |  | Us & GITL
[5 empty] | Mapping of fields | 2026-02-25 | 2026-02-27 | 2026-02-25 | 2026-02-27 | Ananth
[5 empty] | Field wise controls and measures | 2026-02-27 | 2026-03-02 | 2026-02-27 | 2026-03-02 | Ananth
[5 empty] | Coding | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
|  |  |  | Testing |  | 2026-05-11 | 2026-05-15 |  |  | GITL
[5 empty] | Unit tests | 2026-05-11 | 2026-05-13 |  |  | GITL
[5 empty] | UI validation tests | 2026-05-13 | 2026-05-15 |  |  | GITL
|  |  | Backend |  |  | 2026-04-20 | 2026-05-15 | 2026-04-20 |  | GITL
|  |  |  | Backend development |  | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
|  |  |  | API Integration |  | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
[5 empty] | API wise integration | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
[5 empty] | Error & timeout handling | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
[5 empty] | Retry & fallback logic | 2026-04-20 | 2026-05-08 | 2026-04-20 |  | GITL
|  |  |  | Database Schema |  | 2026-04-24 | 2026-05-08 | 2026-04-24 |  | GITL
|  |  |  | Integration with Frontend |  | 2026-04-24 | 2026-05-08 | 2026-04-24 |  | GITL
|  |  |  | Testing |  | 2026-05-11 | 2026-05-15 |  |  | GITL
[5 empty] | Unit tests | 2026-05-11 | 2026-05-15 |  |  | GITL
[5 empty] | API contract tests | 2026-05-11 | 2026-05-15 |  |  | GITL
|  |  | Agents |  |  | 2026-03-12 | 2026-05-22 | 2026-03-12 |  | Digital
|  |  |  | Mapping of agents |  | 2026-03-12 | 2026-03-17 | 2026-03-12 | 2026-03-17 | Digital
|  |  |  | Coding of agents |  | 2026-03-17 | 2026-05-08 | 2026-03-17 |  | Digital
|  |  |  | Coding of individual agents |  | 2026-03-17 | 2026-05-08 | 2026-03-17 |  | Digital
|  |  |  | Combine similar agents wherever possible |  | 2026-04-27 | 2026-05-08 | 2026-04-27 |  | Digital
|  |  |  | Agent Orchestration |  | 2026-05-11 | 2026-05-15 |  |  | Digital
|  |  |  | Agent Testing |  | 2026-05-18 | 2026-05-22 |  |  | Digital
|  | Documentation |  |  |  | 2026-02-11 | 2026-05-22 | 2026-02-11
| Leasing Automation |  |  |  |  | 2026-04-15 | 2026-09-16 | 2026-04-15
|  | Process Mapping |  |  |  | 2026-04-15 | 2026-05-25 | 2026-04-15 |  | Mehrshad Nava
|  |  | Steps till PO Creation |  |  | 2026-04-15 | 2026-05-25 | 2026-04-15 |  | Charit Mehrshad | Metting set with Mikhil sir 30-06
|  |  | Discussion / issue resolving |  |  | 2026-05-11 | 2026-05-25 |  |  | GITL / internal
|  |  | Finalizing Flow |  |  | 2026-04-25 | 2026-05-25 | 2026-04-25 |  | Charit Mehrshad
|  |  | Document flow After PO Ctreation |  |  | 2026-04-15 | 2026-05-25 | 2026-04-15 |  | Mehrshad Nava | Metting set with Mikhil sir 30-06
|  |  |  | Mapping as it Process for Mizuho |  | 2026-04-22 | 2026-04-30 | 2026-04-22 | 2026-04-30 | Mehrshad Nava
|  |  |  | Mapping as it Process ORIX / HPFS |  | 2026-04-22 | 2026-04-30 | 2026-04-22 | 2026-04-30 | Mehrshad Nava
|  |  |  | Finalizing Flow |  | 2026-04-30 | 2026-06-25 | 2026-04-30 |  | Charit Mehrshad
|  | Agent Identification & scope |  |  |  | 2026-05-25 | 2026-05-20 |  |  | Charit Mehrshad
|  |  | First cut of Agentic break |  |  | 2026-05-25 | 2026-05-18 |  |  | Charit Mehrshad
|  |  | Finalization of Agentic break |  |  | 2026-05-25 | 2026-05-20 |  |  | Charit Mehrshad
|  | Discussion with DIGITAL / GITL |  |  |  | 2026-05-30 | 2026-05-30 |  |  | Digital GITL
|  | Development |  |  |  | 2026-06-10 | 2026-08-31 |  |  | Digital GITL
|  |  | Speedflow data access |  |  | 2026-06-10 | 2026-08-31 |  |  | GITL
|  |  | Frontend |  |  | 2026-06-10 | 2026-08-31 |  |  | Digital
|  |  | Backend |  |  | 2026-06-10 | 2026-08-31 |  |  | Digital
|  |  | Agent development |  |  | 2026-06-10 | 2026-08-31 |  |  | Digital GITL
|  | Tesing |  |  |  | 2026-08-31 | 2026-09-15 |  |  | Digital GITL
|  | live |  |  |  | 2026-09-15 | 2026-09-16
eBRC
|  | IEC Branch Mapping |  |  |  | 2026-02-11 | 2026-02-27 | 2026-02-11 | 2026-02-27 | Ivan Charit
|  | Moving current fetching of IRM data to Production |  |  |  | 2026-02-11 | 2026-04-02 | 2026-02-11 | 2026-04-02 | Ivan
|  | Meeting to decide on the final system |  |  |  | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-02-23 | Ivan ananath
|  | Prototype and testing |  |  |  | 2026-03-23 | 2026-04-08 | 2026-03-23 | 2026-04-08 | Ivan ananath
|  | Writing Code |  |  |  | 2026-04-09 | 2026-04-15 | 2026-04-09 | 2026-04-15 | Ivan ananath
|  | Testing |  |  |  | 2026-04-16 | 2026-04-22 | 2026-04-16 | 2026-05-15 | Ivan ananath
|  | Go live |  |  |  | 2026-04-23 | 2026-04-29 | 2026-05-18 |  | GITL |  | planned end date 5th june
Forex
|  | Finalizing dashboard layout for current replica |  |  |  | 2026-02-11 | 2026-02-13 | 2026-02-11 | 2026-02-13
|  | (OTRS) Provision to upload existing contract and other details |  |  |  | 2026-02-11 | 2026-02-12 | 2026-02-11 | 2026-02-12
|  | (SRF) Provision to upload existing contract and other details |  |  |  | 2026-02-13 | 2026-02-15 | 2026-02-13 | 2026-02-15
|  | (New SRF) Provision to upload existing contract and other details |  |  |  | 2026-04-06 | 2026-04-09 | 2026-04-06 | 2026-04-09
|  | (FSD) Provision to upload existing contract and other details |  |  |  | 2026-02-19 | 2026-05-04 | 2026-02-19 | 2026-05-06
|  | Development |  |  |  | 2026-05-13 | 2026-06-12 | 2026-05-13
|  | Building the dashboard as per requirements |  |  |  | 2026-02-16 | 2026-03-13 | 2026-02-16 | 2026-03-13
|  | Added new Dashboard page for MTM |  |  |  | 2026-04-20 | 2026-05-15 | 2026-04-20
|  |  | Normal MTM report as per bank |  |  | 2026-04-20 | 2026-04-24 | 2026-04-20 | 2026-04-24
|  |  | Gain/Loss Report |  |  | 2026-05-04 | 2026-05-08 | 2026-05-04 | 2026-05-08
|  |  | What-If Analysis |  |  | 2026-05-11 | 2026-05-15
| IDPMS Dashboard |  |  |  |  | 2026-05-04 | 2026-06-02 | 2026-05-04 | 2026-06-02 | Charit
|  | Data Mapping |  |  |  | 2026-05-04 | 2026-05-08 | 2026-05-04 | 2026-05-08 | Charit & Vaishanvi
|  | Dashboard 1st Cut |  |  |  | 2026-05-11 | 2026-05-15 | 2026-05-11 | 2026-05-15 | Charit
|  | Changes and Modifications |  |  |  | 2026-05-18 | 2026-05-25 | 2026-05-18 | 2026-05-27 | Charit
|  | Final Testing |  |  |  | 2026-05-26 | 2026-05-29 | 2026-06-01 | 2026-06-03 | Charit & Vaishanvi
|  | Dashboard Live |  |  |  | 2026-06-01 | 2026-06-02 | 2026-06-04 | 2026-06-05 | Charit
Bill of Entry
|  | Process Mapping |  |  |  | 2026-04-29 | 2026-05-10 | 2026-04-29 |  | Mehrshad
|  | Detail extraction using Python Script |  |  |  | 2026-04-29 | 2026-05-10 | 2026-04-29 |  | Mehrshad
|  |  | Fields mapping |  |  | 2026-04-29 | 2026-05-10 | 2026-04-29 |  | Mehrshad
|  |  | Coding |  |  | 2026-05-10 | 2026-05-30 |  |  | Mehrshad
|  |  | Testing |  |  | 2026-05-10 | 2026-05-30 |  |  | Mehrshad
|  | Testing |  |  |  | 2026-05-20 | 2026-05-30 |  |  | Charit
|  | creating flow to run the script |  |  |  | 2026-05-05 | 2026-05-30 |  |  | Charit
|  | Testing |  |  |  | 2026-05-30 | 2026-06-05 |  |  | Charit
|  | live |  |  |  | 2026-06-05 | 2026-06-06 |  |  | Charit
| Bill of Entry Checklist |  |  |  |  | 2026-06-03 | 2026-06-19
|  | Script Developement |  |  |  | 2026-06-10 | 2026-06-15
|  | Script testing |  |  |  | 2026-06-16 | 2026-06-20
| Pre-Import Condition Controls in LN |  |  |  |  | 2026-06-03 | 2026-06-30 | 2026-03-03 | 2026-06-30 | Charit
|  | Problem Discussion and Brainstorming |  |  |  | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-03 | Benefits, Division, Purchase Team
|  | SRF |  |  |  | 2026-06-04 | 2026-06-12 | 2026-06-04 |  | Charit
|  |  | SRF Preparation |  |  | 2026-06-04 | 2026-06-05 |  |  | Charit
|  |  | SRF Raised & Approved |  |  | 2026-06-08 | 2026-06-09 |  |  | Charit
|  |  | SRF CCB Approval & Attach in system |  |  | 2026-06-09 | 2026-06-12 |  |  | Charit
|  | FSD |  |  |  | 2026-06-15 | 2026-06-19 |  |  | GITL
|  |  | FSD Preparation |  |  | 2026-06-15 | 2026-06-17 |  |  | GITL
|  |  | FSD Approval |  |  | 2026-06-18 | 2026-06-19 |  |  | Charit
|  | Infor Developmet |  |  |  | 2026-06-22 | 2026-06-26 |  |  | GITL
|  | UAT |  |  |  | 2026-06-29 | 2026-06-30 |  |  | ALL
|  | Live |  |  |  | 2026-06-30 | 2026-06-30 |  |  | GITL
| Banking API Integration |  |  |  |  | 2026-06-04 | 2026-06-30 | 2026-06-04 |  | Ivan & Ananth
|  | Problem Discussion and Brainstorming |  |  |  | 2026-06-04 | 2026-06-10 | 2026-06-04
| ITR-1 Dashboard |  |  |  |  | 2026-05-25 | 2026-06-12 | 2026-05-25 |  | Ivan
|  | Modifications |  |  |  | 2026-05-25 | 2026-06-12 | 2026-05-25
Steel Dashboard Enhancements
|  | Stockout Decision |  |  |  | 2026-06-09 | 2026-06-30 | 2026-06-09
|  | Rate Comparison |  |  |  | 2026-06-09 | 2026-06-30 | 2026-06-09 |  | Ivan
|  | Hedge Decision |  |  |  | 2026-06-09 | 2026-06-30 | 2026-06-09 |  | Ananth
[6 empty] | 2026-06-09 | 2026-06-30 | 2026-06-09 |  | Ananth